## START HERE
Job Cost Tracker — Small
Creeley Digital Systems · creeleydigital.com.au
Quote vs actual for single-trade and smaller jobs. See your margin in real time.
HOW TO USE THIS WORKBOOK
1. Fill in Job Details first — this information appears in the Summary.
2. On Materials and Labour sheets, enter your quoted amounts before the job starts.
3. Log actual costs as you spend — the Variance columns update automatically.
4. The Summary sheet shows your overall quote vs actual position and gross margin.
5. Add variations on the Summary sheet under the Variations section.
LEGEND — CELL COLOURS
Gold cells — fill these in (your inputs)
Grey-blue cells — auto-calculated, do not edit
Dark cells — totals and summaries
TIPS
💡 Fill in your quoted amounts before the job starts — don't wait until you're halfway through.
💡 Log every receipt as it comes in, not all at the end — it's more accurate and less effort.
💡 Check your margin percentage on the Summary sheet as the job progresses.

## Job Details
Job Details
Creeley Digital Systems · creeleydigital.com.au
Enter job information here before starting.
Job Name / Title
Client Name
Job Number / Reference
Site Address
Job Description
Start Date
Estimated Finish Date
Contract Value (inc. GST)
Project Manager / Supervisor
Client Contact
Notes

## Materials
Materials Register
Creeley Digital Systems · creeleydigital.com.au
Log all materials costs — quoted and actual.
# | Item Description | Supplier | Qty | Unit | Unit Cost (Q) | Budget Total (Q) | Actual Cost | Variance
1 | [5 empty] | 0 |  | 0
2 | [5 empty] | 0 |  | 0
3 | [5 empty] | 0 |  | 0
4 | [5 empty] | 0 |  | 0
5 | [5 empty] | 0 |  | 0
6 | [5 empty] | 0 |  | 0
7 | [5 empty] | 0 |  | 0
8 | [5 empty] | 0 |  | 0
9 | [5 empty] | 0 |  | 0
10 | [5 empty] | 0 |  | 0
11 | [5 empty] | 0 |  | 0
12 | [5 empty] | 0 |  | 0
13 | [5 empty] | 0 |  | 0
14 | [5 empty] | 0 |  | 0
15 | [5 empty] | 0 |  | 0
16 | [5 empty] | 0 |  | 0
17 | [5 empty] | 0 |  | 0
18 | [5 empty] | 0 |  | 0
19 | [5 empty] | 0 |  | 0
20 | [5 empty] | 0 |  | 0
21 | [5 empty] | 0 |  | 0
22 | [5 empty] | 0 |  | 0
23 | [5 empty] | 0 |  | 0
24 | [5 empty] | 0 |  | 0
25 | [5 empty] | 0 |  | 0
26 | [5 empty] | 0 |  | 0
27 | [5 empty] | 0 |  | 0
28 | [5 empty] | 0 |  | 0
29 | [5 empty] | 0 |  | 0
30 | [5 empty] | 0 |  | 0
TOTALS |  |  |  |  | 0 | 0 | 0 | 0

## Labour
Labour Log
Creeley Digital Systems · creeleydigital.com.au
Track hours quoted and actual for each worker.
# | Name / Trade | Role | Hrs Quoted | Rate / hr | Labour Budget | Hrs Actual | Labour Actual | Variance
1 |  |  |  |  | 0 |  | 0 | 0
2 |  |  |  |  | 0 |  | 0 | 0
3 |  |  |  |  | 0 |  | 0 | 0
4 |  |  |  |  | 0 |  | 0 | 0
5 |  |  |  |  | 0 |  | 0 | 0
6 |  |  |  |  | 0 |  | 0 | 0
7 |  |  |  |  | 0 |  | 0 | 0
8 |  |  |  |  | 0 |  | 0 | 0
9 |  |  |  |  | 0 |  | 0 | 0
10 |  |  |  |  | 0 |  | 0 | 0
11 |  |  |  |  | 0 |  | 0 | 0
12 |  |  |  |  | 0 |  | 0 | 0
13 |  |  |  |  | 0 |  | 0 | 0
14 |  |  |  |  | 0 |  | 0 | 0
15 |  |  |  |  | 0 |  | 0 | 0
16 |  |  |  |  | 0 |  | 0 | 0
17 |  |  |  |  | 0 |  | 0 | 0
18 |  |  |  |  | 0 |  | 0 | 0
19 |  |  |  |  | 0 |  | 0 | 0
20 |  |  |  |  | 0 |  | 0 | 0
TOTALS |  |  | 0 |  | 0 | 0 | 0 | 0

## Summary
Job Cost Summary
Creeley Digital Systems · creeleydigital.com.au
Auto-calculated. Check margin before invoicing.
Cost Category | Budget (Quoted) | Actual Cost | Variance
Materials | 0 | 0 | 0
Labour | 0 | 0 | 0
Variations / Other (net) |  |  | 0
TOTAL COSTS | 0 | 0 | 0
JOB FINANCIAL SUMMARY
Contract Value (ex. GST)
Adjusted Contract Value (inc. approved variations) | 0
Total Actual Costs | 0
Gross Profit | 0
Gross Margin % | 0%

## Quote Builder
QUOTE BUILDER & RISK ALLOWANCE
Build a defensible price from quantities, labour, subcontractors, overhead and risk.
HOW TO USE THIS TOOL
1. Enter direct costs using realistic quantities and rates.
2. Use markup for purchasing effort, wastage and commercial risk - not as a substitute for overhead.
3. Enter overhead recovery and contingency separately so assumptions stay visible.
4. Check that the target margin is sustainable before sending the quote.
5. Copy approved budget amounts into the Summary before work starts.
COST BUILD-UP
Cost item | Category | Qty / hours | Unit | Unit cost | Base cost | Markup % | Sell price | Assumption / source
Example: framing timber | Materials | 1 | lot | 2400 | 2400 | 15% | 2760 | Supplier quote dated…
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
| Materials |  |  |  |  | 0%
QUOTE SUMMARY
Direct cost | 2400 | Line-item sell | 2760 | Overhead recovery | 8%
Contingency | 5% | Recommended price | 3129.84 | Target gross margin | 23.32%
GST | 10% | Price inc GST | 3442.824 | Price rounded | 3400
Commercial checks | Confirm scope, exclusions, payment schedule, validity period, access assumptions and variation process.
Approval | Prepared by: |  | Checked by: |  | Date: